## Product_Backlog
ID | User Story | Priority | Status
1 | User selects research paper from dropdown | High | Done
2 | User asks questions about paper | High | Done
3 | System retrieves relevant chunks using FAISS | High | Done
4 | System maintains chat memory | Medium | Done
5 | User uploads new PDF paper | High | Done
6 | System chunks and embeds uploaded paper | High | Done
7 | System summarizes uploaded paper | Medium | Done
8 | Display confidence score for answers | Medium | Done
9 | Split UI for Chat and Summarizer | Medium | Done

## Sprint_Backlog
Sprint | Task | Owner | Status
Sprint 1 | Set up project structure and dependencies | Team | Done
Sprint 1 | Implement PDF text extraction | Team | Done
Sprint 2 | Implement chunking and embeddings | Team | Done
Sprint 2 | Integrate FAISS retrieval | Team | Done
Sprint 3 | Build Gradio UI for chat | Team | Done
Sprint 3 | Add summarizer functionality | Team | Done
Sprint 4 | Add confidence score and improvements | Team | Done

## Retrospective
Sprint | What Went Well | What Could Improve | Action Items
Sprint 1 | Project setup completed quickly | Better documentation | Maintain setup guide
Sprint 2 | Embedding pipeline working | Optimize performance | Precompute embeddings
Sprint 3 | UI functional | Improve response speed | Optimize retrieval
Sprint 4 | All features integrated | Add citations | Future enhancement